## Slide 1: [Project Name]
Status Report
Month XX, 2022
Insert client logo here

## Slide 2: [Project Name] Status Report
July 23, 2022
To Do #1
To Do #2
To Do #3
Key Accomplishments
Next Sprint: Top Priorities
Accomplishment 1
Accomplishment 2
Accomplishment 3
Accomplishment 4
Milestone | Status | Target Date | FCST Date | Comments
Timeline: Upcoming Milestones
Project Status:
Project Risks
Discussion Topics
Item #1
Item #2
Note: This items often have additional pages as needed for deeper discussion
Risk #1
Risk #2
Risk #3

## Slide 3: [Project Name] Status Report
July 23, 2022
Optimization enhancements: PTO Forecast and then Attrition enhancements
Automate data ingestion
Cloud resource identification for additional support
Key Accomplishments
Next Sprint: Top Priorities
Updated optimization model to include shift-level requirements & attrition
Built initial attrition model
Refined wireframe and began building Power BI Dashboards
Updated model to allow for known hires and terms
Timeline: Upcoming Milestones
Project Status:
Project Risks
Discussion Topics
Additional dashboard data needs (See following page)
Requirements sign-off
Discuss attendees for attrition review session
Decision required on cost data by 7/28 to be incorporated into next sprint iteration.
  Impact: Medium
Cloud implementation decision required by 7/30 to avoid project delays
  Impact: High
SAMPLE
Consider Timeline chart on secondary page
Milestone | Status | Target Date | FCST Date | Comments
High-Fidelity dashboard wireframe |  | 7/2 | 7/2 | 
Optimization Results iteration #2 |  | 7/26 | 8/2 | Delayed by 1 week due to XYZ
Dashboard POC complete |  | 7/26 | 7/26 | Need response on ABC
Database Set-up (On-Prem) |  | 7/16 | 7/16 | 
Production Dashboard Demo |  | 8/9 | 8/9 |